## Appendix B
Caledonia Offshore Wind Farm
Offshore Scoping Report
Appendix B: Mitigation Commitment Register
Date: 06/09/2022
Code | Mitigation | Offshore topics
|  | Marine and Coastal Processes | Marine Water and Sediment Quality | Benthic Subtidal and Intertidal Ecology | Fish and Shellfish Ecology | Offshore Ornithology | Marine Mammals and Other Megafauna | Commercial Fisheries | Shipping and Navigation | Marine Archaeology and Cultural Heritage | Military and Civil Aviation | Seascape, Landscape and Visual Impact | Socio-economics, Tourism and Recreation | Climate | Other Human Activities
M-1 | Development of and adherence to a Cable Plan (CaP). The CaP will confirm planned cable routing, burial and any additional protection and will set out methods for post-installation cable monitoring. | P | P | P | P |  |  | P | P | P |  |  |  |  | P
M-2 | Development of and adherence to a Development Specification and Layout Plan (DSLP). The DSLP will confirm the layout and design parameters of the Proposed Development. | P | [6 empty] | P | P
M-3 | Development of and adherence to a Construction Method Statement (CMS). The CMS will confirm construction methods and the roles and responsibilities of parties engaged in construction. It will detail any construction-related mitigation measures. | P |  |  |  | P | [5 empty] | P |  | P | P
M-4 | Scour protection where there is the potential for scour to develop around infrastructure (foundations and cables). | P | P | [6 empty] | P
M-5 | Where practicable, cable burial will be the preferred means of cable protection. Cable burial will be informed by the cable burial risk assessment and detailed within the CaP. | P |  | P | P |  |  | P | P
M-6 | Wind farm infrastructure will be micro-sited, where possible, around any sensitive seabed habitats including Annex I habitat (if present) to avoid any developmental impacts on these conservation features. | P |  | P
M-7 | Suitable implementation and monitoring of cable protection (via burial, or external protection where adequate burial depth as identified via risk assessment is not feasible), as detailed within the CaP. | P |  | P | P
M-8 | Development of and adherence to a Environmental Management Plan (EMP). The EMP will set out mitigation measures and procedures relevant to environmental management, including but not limited to the following topics: Chemical usage, invasive non-native marine species, dropped objects, pollution prevention and contingency planning, and waste management. |  | P | P | P | P | P | [6 empty] | P | P
M-9 | Development of and adherence to a Marine Pollution Contingency Plan (MPCP). The MPCP will identify potential sources of pollution and associated spill response and reporting procedures. |  | P | P | P |  | P |  | P | [5 empty] | P
M-10 | Development of and adherence to a Decommissioning Programme (DP). The DP will outline measures for the decommissioning of the Proposed Development. |  | P | P | P |  |  |  |  | P
M-11 | Development of and adherence to a Piling Strategy (PS) (applicable where piling is undertaken). The PS will detail the method of pile installation and associated noise levels. It will describe any mitigation measures to be put in place (e.g., soft starts and ramp ups, use of Acoustic Deterrent Devices) during piling to manage the effects of underwater noise on sensitive receptors. |  |  |  | P | P | P
M-12 | Development of and adherence to a Project Environmental Monitoring Programme (PEMP). The PEMP will set out commitments to environmental monitoring in pre-, during and post-construction phases of the Proposed Development. |  |  |  | P | P | P | P | P |  |  |  |  | P
M-13 | Development of and adherence to a Vessel Management Plan (VMP). The VMP will confirm the types and numbers of vessels that will be engaged on the Proposed Development, and consider vessel coordination including indicative transit route planning. |  |  |  |  | P | P |  | P |  |  | P | P
M-14 | Development of and adherence to a Lighting and Marking Plan (LMP). The LMP will confirm compliance with legal requirements with regards to shipping, navigation and aviation marking and lighting. |  |  |  |  | P |  | P | P |  | P | P | P |  | P
M-15 | Blade clearance of at least 35 m above Mean Sea Level (MSL) (minimum blade clearance of 35 m will be maintained for floating WTGs due to tidal movements). |  |  |  |  | P |  |  | P
M-16 | Development of and adherence to Marine Mammal Mitigation Plan (MMMP). This will identify appropriate mitigation measures during offshore activities that are likely to produce underwater noise and vibration levels capable of potentially causing injury or disturbance to marine mammals. This will be developed alongside the PS and referred to in European Protected Species (EPS) licence applications. | [5 empty] | P
M-17 | Development of and adherence to a Fisheries Management and Mitigation Strategy (FMMS). The FMMS will set out the means of ongoing fisheries liaison through construction and operation and maintenance (O&M) phases of the Proposed Development and detail any mitigation measures to be put in place to limit effects on commercial fisheries activity. This will include the following project policies: Fisheries Liaison Policy and Engagement Schedule, Conflict Avoidance Policy, Incident Response Policy. | [6 empty] | P | P
M-18 | Appointment of a Company Fisheries Liaison Officer (CFLO). The CFLO will support ongoing liaison and ensure clear communication between the Proposed Development and Commercial Fisheries. | [6 empty] | P
M-19 | Development of and adherence to a Navigational Safety Plan (NSP). The NSP will describe measures put in place by the Proposed Development related to navigational safety, including information on Safety Zones, charting, construction buoyage, temporary lighting and marking, and means of notification of Project activity to other sea users (e.g., via Notice to Mariners). | [6 empty] | P | P |  |  |  | P |  | P
M-20 | Adherence to best practice guidance with regards to fisheries liaison and procedures in the event of interactions between the Proposed Development and fishing activities (e.g., FLOWW, 2014; 2015). | [6 empty] | P
M-21 | Advance warning and accurate location details of construction, maintenance and decommissioning operations, associated Safety Zones and advisory passing distances will be given via Notices to Mariners and Kingfisher Bulletins. | [6 empty] | P | P |  |  |  | P |  | P
M-22 | Participation in any fisheries working group to assist with liaison between the Proposed Development and the fishing community. | [6 empty] | P
M-23 | Application for and use of Safety Zones of up to 500 m during construction, major maintenance and decommissioning phases. Where appropriate, guard vessels will also be used to ensure adherence with Safety Zones or advisory passing distances, as defined by risk assessment, to mitigate any impact which poses a risk to surface navigation during construction, maintenance and decommissioning phases. Such impacts may include partially installed structures or cables, extinguished navigation lights or other unmarked hazards. | [6 empty] | P | P | [5 empty] | P
M-24 | Any objects dropped on the seabed during works associated with the Proposed Development will be reported and objects will be recovered where they pose a hazard to other marine users and where recovery is possible. | [6 empty] | P | [6 empty] | P
M-25 | Development of and adherence to a Emergency Response Cooperation Plan (ERCoP). The ERCoP will be prepared in line with MCA guidance and confirms what measures the Proposed Development has in place to support any emergency response. | [7 empty] | P |  | P |  |  |  | P
M-26 | Marine coordination and communication to manage project vessel movements. | [7 empty] | P | [5 empty] | P
M-27 | Compliance with Maritime and Coastguard Agency (MCA) Marine Guidance Note (MGN) 654 (MCA, 2021) and its annexes where applicable. Also MGN 543 Search and Rescue (SAR) annex 5 (MCA, 2018). | [7 empty] | P
M-28 | Appropriate marking of the Proposed Development on Admiralty and aeronautical charts. This will include provision of the positions and heights of structures to the UK Hydrographic Office (UKHO), Civil Aviation Authority (CAA), Ministry of Defence (MoD) and Defence Geographic Centre (DGC). | [7 empty] | P |  | P
M-29 | The construction area will be buoyed, as described in the NSP. Buoyage will be defined in consultation with the Northern Lighthouse Board (NLB). | [7 empty] | P
M-30 | Marine navigation marking and lighting of the Project, as described in the LMP, will be defined in agreement with NLB and in line with International Association of Lighthouse Authorities (IALA) Recommendation O-139 (IALA, 2013). | [7 empty] | P |  |  | P
M-31 | Compliance with regulatory expectations on moorings for floating wind and marine devices (Health and Safety Executive (HSE) and MCA, 2017). | [7 empty] | P
M-32 | Development of and adherence to a Written Scheme of Archaeological Investigation (WSI). The Marine WSI will include the implementation of a Protocol for Archaeological Discoveries (PAD) in accordance with ‘Protocol for Archaeological Discoveries: Offshore Renewables Projects’. | [8 empty] | P
M-33 | Seabed preparation, installation activities and installed infrastructure will avoid any identified seabed heritage assets and anthropogenic geophysical anomalies identified as Archaeological Exclusion Zones and described in the WSI. | [8 empty] | P
M-34 | Aviation lighting and marking, as described in the LMP, will be installed in accordance with Article 223 of Civil Aviation Publication (CAP) 393, the UK Air Navigation Order (ANO) 2016 which sets out the mandatory requirements to be followed for lighting of offshore Wind Turbine Generators (WTGs). | [9 empty] | P | P
M-35 | The layout of the Proposed Development, as presented in the DSLP, will be finalised in discussion with the MCA and the NLB in order to ensure the specific WTG layout is compatible with potential Search and Rescue activity. | [9 empty] | P
M-36 | Failures to Proposed Development lighting and marking will be appropriately reported and rectified as soon as practicable. Interim hazard warnings will be put in place as required. | [9 empty] | P
M-37 | The layout of the Project, as presented in the DSLP, will be finalised to ensure, as far as practicable, the reduction of seascape, landscape and visual effects on the closest coastal receptors. | [10 empty] | P
M-38 | Crossing and proximity agreements with known existing pipeline and cables operators will be sought. | [13 empty] | P