## Marine Licence App
Marine Licence App
Section | Question | Cierco Comment
1 | Project Title and Payment Details | The Forthwind Test Site. Installation and operation of 1 offshore wind turbine on the northern shore of the Firth of Forth at Methil, Scotland.
2 | Applicant Details | Mrs G Lee Forthwind Ltd, The Boathouse, Silverhands, Hawkcraig Road, Aberdour, Fife, KY3 0TZ SC 47 05 80 Gemma.lee@ciercoenergy.com
3 | Agent Details (if any) | n/a
4 | Duration of Project | Start date: TBC, Expected completion date: TBC
5(a) | Description and Cost of the proposed Project Estimated gross cost of the works proposed seawards of the tidal limit of MHWS | The value of the offshore installation works is anticipated to be in the region of £9M and the value of the export cable installation is anticipated to be up to £5M.
5(b) | Description and Cost of the proposed Project Give a detailed description of the proposed schedule of work. | The offshore installation will take place over a 3 to 6 month period, after which the offshore turbine will undergo a period testing and commissioning before becoming operational. For a detailed description of the proposed works and indicative schedule of work please refer to Chapter 3 - Project Description of the Forthwind Test Site Environment Impact Assessment Report.
5(c) | Types of work proposed General Marine Project (e.g. wave, tidal device, monopile turbine) | General Marine Project - Offshore wind turbine
| Scientific/ Marine Survey (e.g. geotechnical, geophysical, waverider) | None
| Moorings (e.g. private, commercial): | A boat mooring and landing system will be located on the turbine tower (at sea level) to allow access
| Dredging / Drilling operations | Piling for either x4 pin piles, or one 10m monopile, and small scale drilling operations (rock anchors, stabilising rock anchors, stabilising rock anchors for pipelines etc.) as part of the General Marine Project – Offshore Wind
6 | Location of Project (including any temporary deposit locations | Turbine: 337812, 697333 Temporary MetMast: 337314, 696959
7 | Method Statement | For detail, please refer to Chapter 3: Project Description of the Forthwind Demonstration Site Environment Impact Assessment Report (EIAR) submitted with this marine licence application which includes a detailed project description (including expected installation methods) and environmental impact assessment results. The sequence of works undertaken to install the offshore wind turbine is detailed in Chapter 3: Project Description of the EIAR and includes; preparation work, foundation installation, export cable installation, turbine installation, and commissioning. Construction will take place over a three to six month period.
8(a) | Quantity of permanent (and temporary, where applicable) materials to be deposited below MHWS) | Type of deposit | Deposit Quantity | Deposit Quantity per Foundation Option
|  | Steel/iron | 4190 | Monopile Pile:1514 tons TP: 564 tons = 1979 tons Jacket Pile: 297X4= 1188 tons Sleeve: 95X4=380 tons Substructure=2000 tons = 3568 tons MetMast Pile: 418 tons TP: 204tons = 622 tons | For the purposes of the Marine Licence, we are looking to submit an application for the maximum-scenario design for deposit quantities (Column C). The foundation options include monopile and pin pile (jacket design). The maximum deposit quanity of steel/iron, concrete, stone/rock/gravel, and concrete bags/ mattresses will vary between the foundation options. Details regarding both foundation options have been included for information purposes. Monopile Including the entire TP (which goes above the MHWS) we get a steel mass of 564 tons. But including the TP only up to the MHWS i.e. 12.6m we get a steel mass of (pi/4)*[10.5^2-10.3^2]*12.6*7.85= 324 tons. Grout between the TP and the monopile (for an overlap length of 10m) = (pi/4)*[10.30^2-10.00^2]*10=47.84m3 Monopile will be drilled so there will be grout in between the pile and ground. Assuming a standard annulus thickness of 150mm I estimate a grout volume = (pi/4)*[10.30^2-10.00^2]*40=191.32m3 Assuming a higher annulus thickness of 300mm I get a grout volume = (pi/4)*[10.60^2-10.00^2]*40=388.30m3 Jacket - Pile steel is 283*4=1132 tons Sleeve steel is 95*4=380 tons Pile-ground Piles will be drilled so there will be grout in between the pile and ground. Assuming a standard annulus thickness of 150mm I estimate a grout volume = (pi/4)*[3.8^2-3.5^2]*40=68.8m3 per pile; and 68.8X4=275.2m3 total. Assuming a higher annulus thickness of 300mm I get a grout volume = (pi/4)*[4.1^2-3.5^2]*40=143.26m3 per pile; and 143.26X4=573.04m3 total. Jacket-pile The jacket-leg will be fixed inside the pile. Assuming a stab-in length of 10m and a standard annulus thickness of 150mm I estimate a grout volume = (pi/4)*[3.34^2-3.04^2]*10=15.04m3 per pile. I need to add extra grout for the stab-in cone (which I assume to have a length of 1m) area=2/3*pi*(3.34/2)^2*1=5.84m3 . so that’s 15.04+5.84=20.88m3per pile; and 20.88X4=83.52m3 total. Assuming a higher annulus thickness of 300mm I get a grout volume = (pi/4)*[3.34^2-2.74^2]*10=28.66m3 + 5.84m3=34.5m3 per pile; and 34.5X4=138 m3 total. MetMast Including the entire TP (which goes above the MHWS) we get a steel mass of 204 tons. But including the TP only up to the MHWS i.e. 12.6m we get a steel mass of (pi/4)*[3.86^2-3.66^2]*12.6*7.85= 116.84 tons. Grout between the TP and the pile (for an overlap length of 10m) = (pi/4)*[3.76^2-3.46^2]*10=17.02m3. Scour and Filler The jacket pile will have to be filled up the silt/sand. It isn’t special stuff, just material to fill up to the stab-in length; otherwise we’ll be filling up the entire pile with grout and that is not cost effective. Volume of filler material = (pi/4)*3.34^2 *(42-5)=324.18m3. (I have assumed a stab in length of 5m.); and 324.18X4=1296.72m3 total. Scour protection strategy may include rock/gravel or concrete bags/mattresses. For all cases I’ve assumed that the scour hole depth is 1.3X pile OD and the scour hole radius is 5X pile OD and that the scour protection material fills up the scour hole. Monopile: 1/3*pi*(5*10)^2*(1.3*10)=34034m3 Jacket: 1/3*pi*(5*3.5)^2*(1.3*3.5)=1460m3 per pile. Assuming a leg-to-leg length of 20m the total is 3X1460+(20*20*(1.3*3.5))=6200m3 Metmast-pile: 1/3*pi*(5*3.5)^2*(1.3*3.5)=1460m3
|  | Concrete | 874 | Monopile Pile-ground:389m3 Pile-TP: 48m3 = 437 m3 Jacket Pile-ground: 574m3 Leg-Pile: 138m3 =712 m3 MetMast Pile-ground:144m3 Pile-TP: 18m3 = 162 m3
|  | Stone / Rock/ Gravel | 1297 | Jacket Pile Filler: 1297m3
|  | Concrete bags / mattresses | 34034 | Monopile 34034m3 Jacket 6200m3 MetMast 1460m3
|  | Cable | 2425
8(b) | Method of delivery of material (see guidance notes) | By vessel, no further details or route are known at present. Please see Chapter 3: Project Description of the Forthwind Environmental Impact Assessment Report).
12 | Duration of Dredging/ Drilling Operation When is it proposed to begin the dredging/drilling operation? | TBC
| When are dredging/drilling and disposal operations expected to be completed? | TBC
13 | Details of Dredging/Drilling and Disposal Vessel(s) | Name of vessel and operator: TBC Type of Vessel: TBC
14 | Method Statement for Dredging/Drilling Operation | Drilling installation methods included within Chapter 3: Project Description, Section 3.6 of the EIAR.
15 | Use of Explosives Will any part of the dredging operation involve the use of explosives | N/A
16 | Details of Areas to be dredged/drilled | Turbine 1 - 337812, 697333 - Pile drill Cable route - trench dimensions 3 x 1.5 m (where trenching is possible) Metmast - 337314, 696959 - pile drill
17 | Details of Material to be Dredged / Drilled | TBC
19 | Details of Dredged Material Quality Has the dredged/drilled material been chemically analysed in the alst 3 years? Can the samples be made available if required | No N/A
20 | Best Practicable Environmental Option (BPEO) Assessment Has an up to date BPEO assessment been included with your application | No
23 | Statutory Consenting Powers Do you, or (if appropriate) your client, have statutory powers to consent any aspect of this project? | No
24 | Advertising and Consultation Have these proposals been advertised to the public? | 1. Ongoing consultation with local stakeholders and key consultees. 2. Distribution of the Scoping Report to consultees. 3. A pre-application consultation event was held at The Hydrogen Office, Ajax Way, Methil Docks, KY8 3RS between the hours of 11:00 am and 7 pm on Monday 13th December 2021. The event was advertised in advance in the East Fife Mail (on 27th October) which is circulated in the vicinity of the Proposed Development.
| Have the public been invited to submit comments? | Yes, comments and questions relating to any aspect of the Proposed Development were invited from all visitors who attended the Public consultation event in December 2021. The Consultation Event Public Notice invited persons wishing to provide comments on the proposed development to do so by writing to gemma.lee@cierco.uk or by post to Forthwind Ltd. Quayside House, Dock Road, Methil Docks, KY8 3SR, not later than Friday 17th December 2021, although no written questions have been put forward to date.
| Have any consultation meetings with the public been arranged? | A pre-application consultation event was held at the Hydrogen Office, Ajax Way, Methil Docks, KY8 3RS between the hours of 11:00 am and 7:00 pm on Monday 13th December 2021.
25 | Consultation with Conservation Bodies Provide details of any consultation with Conservation Bodies, and, if appropriate, include copies of any correspondence with your application. | A Scoping Request was issued to MS-LOT on 4th August 2021. A Scoping Opinion was received on 24th December. Table 2.1 of the Forthwind Ltd Test Site Environment Impact Assessment Report provides an overview of the issues raised by the consultees in response to the 2021 scoping request. The detail of the individual responses recieved from the consultees during the EIA process, including the scoping stage is set out in the relevant technical chapters of the EIAR. A Scoping "gap analysis" is provided as part of the Marine Scotland application submission process, detailing how each consultee response has been addressed within Proposed Development.
26 | Designated Conservation Areas | Firth of Forth SPA, RAMSAR, SSSI sites adjacent to terrestrial parts of Development and 1.2 km from turbine location
| If yes, indicate approximate distance of the operations from the boundary of the nearest conservation area | The cable corridor is within the Firth of Forth conservation areas identified above.
27 | Is the EIA/ES available for public inspection? If YES at what locations? | 1. Forthwind Ltd. Office, The Baothouse, Silversands, Hawkcraig Road, Aberdour, Fife, KY3 0tz